## Retroplanning course production
Production planning {name of the course} |  | 2018-04-02 | 2018-05-03 |  |  | 7 | 7
PHASE > Task | 👤 | ℹ️ | End 🗓 | ⌛️ | 📥 Deliverable | 🚦Status | 🔬Review | 2018-04-02 | 2018-04-09 | 2018-04-16 | 2018-04-23 | 2018-04-30 | 2018-05-07 | 2018-05-14 | 2018-05-21 | 2018-05-28 | 2018-06-04 | 2018-06-11 | 2018-06-18 | 2018-06-25 | 2018-07-02 | 2018-07-09 | 2018-07-16 | 2018-07-23 | 2018-07-30 | 2018-08-06 | 2018-08-13 | 2018-08-20
ANALYSIS | bar: 2018-04-02; 2018-06-18 to 2018-08-20
Research the topic | Instructional designer |  |  |  |  | 😃Early
🔍 Study the need | Teacher + Edtech Company |  |  | 2h | Séquençage pédagogique
🔭 Quick benchmark | Teacher |  |  | 1h | Séquençage pédagogique
🕵️ Thorough benchmark | Instructional designer |  |  | 1j - 2j
🎯 Define a skill set | Teacher + Edtech Company |  |  | 3h | Séquençage pédagogique
🔗 Identify pre-requisites | Teacher |  |  | 30min | Séquençage pédagogique
🗓 Draft the production planning | Teacher + Edtech Company |  |  | 30min | This template
DESIGN | bar: 2018-04-02; 2018-06-18 to 2018-08-20
📏 Expand the skill set into a course outline | Teacher + Edtech Company |  |  | 1j
💡 Creative meeting with the video team | Teacher + Edtech Company |  |  | 1h
🗓 🎥 Request a video shooting | Edtech Company |  |  | 15min
🗓 Adjust the production planning | Edtech Company |  |  | 30min
EDITORIAL PRODUCTION
✍️ Write the course introduction | Teacher |  |  | 3h | {Course URL}
✍️ Write the first chapter | Teacher |  |  | 1j | {Course URL}
✍️ Write part 1 | Teacher |  |  | 3-4j | {Course URL}
📝 Create assessments for part 1 (quizz, P2P activities) | Teacher |  |  | 1j | {Course URL}
✍️ Write part 2 | Teacher |  |  | 4j | {Course URL}
📝 Create assessments for part 2 (quizz, P2P activities) | Teacher |  |  | 1j | {Course URL}
✍️ Write part 3 | Teacher |  |  | 4j | {Course URL}
📝 Create assessments for part 3 (quizz, P2P activities) | Teacher |  |  | 1j | {Course URL}
VIDEO PRODUCTION
🎬 Write the script of the teaser | Teacher |  |  | 3h
🎬 Write the scripts (semi-improvisation or prompter) | Teacher |  |  | Xj
🗣 Media training session | Teacher + Media trainer |  |  | 3h
💻 🎤 Record screencasts (if needed) | Teacher |  |  | Xj
🎥 Shooting day | Teacher + Video manager |  |  | 6h
💬 Review and comment the videos | Teacher + Video team + Instructional designer |  |  | 4h
IMPLEMENT
🖍 Review ortho-typo | Edtech Company |  |  | 5h
👥 Beta-test the course | > 3 learners
🚀 Launch the course | Edtech Company |  |  | 1h
📣 Inform #marketing, #sales, #education, mentors and partners about the launch of the course | Edtech Company
EVALUATE
📊 Perform a retrospective | Edtech Company |  |  | 3h
🗓 Plan the maintenance | Edtech Company

## Séquençage pédagogique
👩‍🏫 {Titre du cours}👨‍💻👩‍💻
🗣 Audience cible For... | {audience cible n°1} {audience cible n°2} {audience cible n°3}
🎯 Sous-compétences À la fin du cours l'apprenant sera capable de... | [verbe d'action] + [objet de l'action] + [contexte de l'action]
[verbe d'action] + [objet de l'action] + [contexte de l'action]
[verbe d'action] + [objet de l'action] + [contexte de l'action]
[verbe d'action] + [objet de l'action] + [contexte de l'action]
[verbe d'action] + [objet de l'action] + [contexte de l'action]
🔭 Benchmark. | {cours / livres / webinar / white papers / videos similaires} {cours / livres / webinar / white papers / videos similaires}
💪 Aspects différenciants A l'avantage d'être... | - un atelier professionalisant 100% e ligne incorporant la vue macroscopique et théorique du cours et la vue miscropique du tutoriel ultra pratique et guidé - à travers la perspective de l'analyste et du marketing manager en charge de la mise en place d'un SIM - aboutit à un à certificat de réussite - prépare à la réalisation d'un projet professionalisant dans le cadre d'un parcours diplômant
Partie / Compétence 1 :
Chapitre n° | Titre | Synthèse | Nature du contenu | Format principal | Durée max
1.1
1.2
1.3
1.4
🎯 Evaluation 1.
Total :
Partie / Compétence 2 :
Chapitre n° | Titre | Synthèse | Nature du contenu | Format principal | Durée max
2.1
2.2
2.3
2.4
🎯 Evaluation 2.
Total :
Partie / Compétence 3 :
Chapitre n° | Titre | Synthèse | Nature du contenu | Format principal | Durée max
3.1
3.2
3.3
3.4
🎯 Evaluation 3.
Total :
Partie / Compétence X :
Chapitre n° | Titre | Synthèse | Nature du contenu | Format principal | Durée max
4.1
4.2
4.3
4.4
🎯 Evaluation 4.
Total :